## Table A Discounted total fund
Category of total discounted cost by funding source | £m
LUF Funding | 10840880.552
Other Public Sector Funding | 995856.689
Private Sector Funding | 0
Total | 11836737.241
Assumptions
2021/2022 prices
24% Optimism Bias

## Table B Discounted Benefit
Catergory of benefit | £m
Residential land value uplift (LVU) | 23728561.1613
Labour Supply Benefits | 821683.7857
Pedestrian movement benefits | 3317715.8112
Rateable Land Value Uplift | 1448373.8689
Total | 29316334.6271
Assumptions
2021/2022 prices
24% Optimism Bias

## Table C Funding Profile
Funding Sources | 2021-22 | 2022-23 | 2023-24 | 2024-25 | Total
UKG Funding Sought | 600983 | 2999679.4333 | 5935872.6061 | 0 | 9536535.0394
Local Authority Contribution | 70000 | 349390.183 | 691385.7504 | 0 | 1110775.9334
Third Party Contribution | 0 | 0 | 0 | 0 | 0
Total | 670983 | 3349069.6163 | 6627258.3565 | 0 | 10647310.9728

## Table D Costing estimates
Cost heading | Costs (£) | Date Estimated | Status
Park Garden East | -720821.6918 | 2021-06-01 | Outline Design
Events Space | -863498.136 | 2021-06-01 | Outline Design
Bowls & Garden | -2315791.136 | 2021-06-01 | Outline Design
Rockwater Garden | -137349.0816 | 2021-06-01 | Outline Design
Courts & Pitches East | -701657.0393 | 2021-06-01 | Outline Design
Courts & Pitches West | -1350079.3656 | 2021-06-01 | Outline Design
Park Garden West | -930575.287 | 2021-06-01 | Outline Design
Skate & Pump | -3068554.4924 | 2021-06-01 | Outline Design
Hove Lagoon | -558984.7432 | 2021-06-01 | Outline Design

## Table E Delivery Milestones
Dates
Works Activity | Estimated Date | Opening Date | Completion of works (if different)
(components of the Kingsway to the Sea scheme)
Park Garden East | 2021-07-01 | 2024-03-01 | Same as Opening Date
Events Space | 2021-07-01 | 2024-03-01 | Same as Opening Date
Bowls & Garden | 2021-07-01 | 2024-03-01 | Same as Opening Date
Rockwater Garden | 2021-07-01 | 2024-03-01 | Same as Opening Date
Courts & Pitches East | 2021-07-01 | 2024-03-01 | Same as Opening Date
Courts & Pitches West | 2021-07-01 | 2024-03-01 | Same as Opening Date
Park Garden West | 2021-07-01 | 2024-03-01 | Same as Opening Date
Skate & Pump | 2021-07-01 | 2024-03-01 | Same as Opening Date
Hove Lagoon | 2021-07-01 | 2024-03-01 | Same as Opening Date

## Table F Bid Monitoring and Eval
Measure | Data To be used | Baseline data source | Data collection methods | Frequency of data collection | Benefit owner (if Applicable)
Inputs
Funding through LUF | Receipt of funding | Grant award | BHCC Civica system | Post scheme completion | BHCC
Funding through BHCC | Allocation of funding from capital programme | Approved Capital Programme (part of annual accounts) | BHCC Civica system | Post scheme completion | BHCC
Programme management support employed | BHCC timesheets | N/a | BHCC payroll system | Post scheme completion | BHCC
Outputs
Kingsway to the Sea - scheme delivered as per proposal | Health and safety file, as built drawings, completion certificate | LUF Application | Reporting during governance process | Post scheme completion | BHCC
Outcomes
Visitors to the West Hove Seafront - pedestrians | Footfall data | BHCC footfall data | Pedestrian counts | 1 year post scheme completion | BHCC
Visitors to the West Hove Seafront - cyclists | Traffic count data | BHCC annual traffic count data - ATC Site 963 | Traffic counts | 1 year post scheme completion | BHCC
Visitors to sports facilities in the area | Club visitor data | Club visitor data | Club visitor data | 1 year post scheme completion | BHCC
New employment at the West Hove Seafront | Employment data from operators | Employment data from operators | Businesses to complete | 1 year / 3 year post scheme completion | BHCC
Safeguarded employment at the West Hove Seafront | Employment data | Employment data from operators | Businesses to complete | 1 year post scheme completion | BHCC
Visitor satisfaction with recreational and leisure experience | Survey data from stakeholder group meetings | BHCC surveys with community groups | BHCC surveys with community groups | 1 year post scheme completion | BHCC
Accessibility to recreational opportunities for particular groups with protected characteristics | Survey data from stakeholder group meetings | BHCC surveys with community groups | BHCC surveys with community groups | 2 year post scheme completion | BHCC
Participation in physical activity at ward level | NHS intelligence/BHCC Public Health | NHS intelligence/BHCC Public Health | Desk-based research | 3 year post scheme completion | BHCC
Impacts
Vibrant local business environment through increased attractiveness of West Hove as a visitor destination.​ | Business rates in the area | Valuation Office Agency | Desk-based research | 3 year post scheme completion | BHCC
Re-establishing West Hove Seafront as a centre for sports and leisure | Number of users and memberships of sports clubs | Data reported by local clubs | In person surveys, desk based | 3 year post scheme completion | BHCC
Expanding tourism offer away from Central Brighton towards the West Hove Seafront | Cambridge Model approach: survey data, footfall data | Tourism South East Economic Impact Assessment 2019 | In person surveys, desk based | 3 year post scheme completion | BHCC
Improving the Living Environment Deprivation score for the most deprived wards in Wish, Westbourne and South Portslade | Office for National Statistics, English indices of deprivation | Office for National Statistics, English indices of deprivation 2019 | Desk based | 3 year post scheme completion | BHCC
Better connectivity between West Hove, Central Hove and Brighton | Traffic count data | BHCC annual traffic count data between ATC Site 22 and ATC Site 951 | Desk based | 3 year post scheme completion | BHCC