## Sheet1
Table 2.2 Progress on Measures to Improve Air Quality
Measure No. | Measure Title | Category | Classification | Year in AQAP | Estimated Completion Date | Organisations Involved | Funding Source | Defra AQ Grant Funding | Funding Status | Estimated Cost of Measure | Measure Status | Reduction in Pollutant / Emission from Measure | Key Performance Indicator | Progress to Date | Comments / Barriers to Implementation
1a | Active Travel Access | Promoting Travel Alternatives | Intensive active travel campaign & infrastructure | 2018 | 2027 | BHCC City Services | Active Travel England (DfT), BHCC | NO | Funded | £1 million - £10 million | Implementation | Estimated 1 to 5 µg/m3 reduction in NO2 long term (measured as an annual mean at roadside) | Increases in walking and cycling levels, aim for safer active travel environments reduced collisions /casualties, increased active travel kms. | Local Cycling and Walking Infrastructure Plan approved in 2022. Construction underway for Valley Gardens Phase 3, Review of design for A259 active travel scheme. Design for Phase 1 of A23 active travel scheme finalised. | Aim is to reduce numbers of vehicle trips on the road. The Public Health team are currently delivering a Let’s Get Moving Strategy. Aim to increase food deliveries by push bike or e-bike.
1b | Expanded bikeshare scheme and inclusion of e-bikes with the scheme | Promoting Travel Alternatives | Intensive active travel campaign & infrastructure | 2018 | 2027 | BHCC City Services, Beryl Bikes | DfT, BHCC, Beryl Bikes and sponsor | NO | Funded | £500k - £1 million | Completed | Estimated to be 1µg/m3 based on medium uptake, rising to more with high uptake and encouragement of lasting behavioural and lifestyle change | Increased usage and kms, cross-boundary connectivity Access to push bike and e-bike share scheme, for short journeys with options to ride outside the local authority, connecting with the national cycle network | The BTN Bike share scheme was relaunched on 31 March 2023. In the past year, 1.5 million kilometres have been travelled by users. The total fleet is now 780, with 60% being e-bikes and 40% pedal-only bikes. Consultation continues additional bike hubs. | Planned to expand scheme to West Sussex including through B&H AQMA3 in Portslade.
1c | On street bike storage | Alternatives to private vehicle use | Other | 2018 | 2027 | BHCC City Services | BHCC | NO | Funded | £100k - £500k | Completed | Estimated to be <1µg/m3 city centre. Assuming a reduction in diesel vehicle trips. | Increased secure bicycle parking facilities. More local trips by active travel. | 150 cycle hangars now installed. Providing 900 secure spaces for residents. Hangars provide on-street parking for up to 6 bikes in a covered, secure and accessible facility. | The contractor will manage 150 hangars.
1d | Encourage and facilitate home working and remote access to health, services and education | Promoting Travel Alternatives | Encourage / Facilitate homeworking | 2019 | 2027 | Citywide Businesses and public sector bodies | Various | NO | Funded | £50k - £100k | Implementation | Estimated to be 1µg/m3 to 2µg/m3 NO2 avoided, depending on the number of diesel trips saved and the timing of peak road demand that risks congestion, if working shift patterns are not spread out. | Less travel overall, reduced number of vehicle trips and kms | Changes in working and commuting patterns continue since Covid-19. | Brighton's 24-hour economy is not limited to one shift pattern. This helps to spread the demand for travel and reduce the risk of congestion and simultaneous road traffic emissions, happening at the same time.
1e | Lift share and car club /hire | Alternatives to private vehicle use | Car & lift sharing schemes | 2018 | 2027 | Citywide Businesses and local communities | Commercial, developers | NO | Funded | £500k - £1 million | Implementation | Car clubs need to increase percentage of zero emission vehicles, to further reduce NO2 and secondary PM nitrates | Increased use of car club vehicles, reduced car ownership. Electric Brighton car share. | Positive uptake with SMEs and households | Ongoing and established car club operated by Enterprise, with approx. 90 bays/vehicles
1f | Bus access improvements | Transport Planning and Infrastructure | Bus route improvements | 2015 | 2027 | BHCC City Services, Bus Operators. | BHCC, BSIP (DfT), Bus Operators | NO | Funded | > £10 million | Implementation | Progress beyond bus-ULEZ to a higher percentage of zero capable is required. | Cleaner buses, resulting in lower emissions from end of tail pipe. Increase passenger numbers, increase bus passenger kms, increase customer satisfaction. | Bus Service Improvement Plan (BSIP) refresh. Enhanced Bus Partnership between bus operators, BHCC City Transport. Successful £2.9m Tranche 2 Zero Emission Bus Regional Area (ZEBRA2 and ZEBRA3) Red Routes for Lewes Road and London Road approved in December 2023. Red routes also planned for Western Road | Aim to achieve at least pre-Covid passenger usage levels by 2025. Essential to achieve minimum euro-VI buses throughout the city by mid-2025.
1g | Transport Interchanges | Transport Planning and Infrastructure | Public transport improvements-interchanges stations and services | 2018 | 2025 | BHCC City Services, Bus Operators, Train operators, Network Rail | BHCC, BSIP (DfT), Bus Operators, Network Rail | NO | Funded | £1 million - £10 million | Completed | Substantial decreases in NO2 outside Brighton railway station, that is part of AQMA1- A2010. | Increased public transport use, reduced vehicle trips | Brighton railway station bus connections completed. Air quality improved faster than the city and UK average | Achieving pre-Covid bus usage levels. Taxi pick moved from station frontage saving vehicle trips Surrey Street Queens Road and AQMA1-A2010.
1i | School Travel Plans | Promoting Travel Alternatives | School Travel Plans | 2018 | 2027 | BHCC City Services, Sussex Partners and Sustrans working with Education providers | BHCC | YES | Partially Funded | £100k - £500k | Implementation | Estimated to be <1µg/m3. | Fewer car trips and emissions, increased active travel journeys | Ongoing | Long term schemes involving schools, colleges and universities.
1j | Workplace Travel Plans | Promoting Travel Alternatives | Workplace Travel Planning | 2022 | 2027 | BHCC City Services working with Businesses | BHCC and local businesses | NO | Funded | £100k - £500k | Implementation | Estimated to be <1µg/m3. | Fewer car trips and emissions, increased active travel journeys | Ongoing | Helped by flexible working at home since 2019/20 and spreading of journeys to diminish AM PM peak flows linked to rush hour.
1k | School Streets | Promoting Travel Alternatives | Workplace Travel Planning | 2018 | 2027 | BHCC City Services working with schools and Children, Families & Learning | BHCC | NO | Funded | £100k - £500k | Implementation | Minor benefit where air quality is currently good | Increased active travel, aims to reduced vehicle trips, reduce d collisions/casualties and emissions | Six schemes per year, help to deliver safer and improved environments around schools | Ensure active and ongoing engagement with local communities. Extra monitoring planned. Most local schools have good air quality
1l | Continue emission-based charges for resident parking permits | Environmental Permits | Introduction/increase of environment charges through permit systems and economic instruments | 2022 | 2027 | BHCC City Services, including Parking | BHCC Parking and income | NO | Funded | £100k - £500k | Implementation | Trace levels | Aim for a higher number of ultralow and zero vehicle permits purchased | Controlled parking zones are focussed on central/busy areas concurrent with AQMA reduces risk of vehicles circulating to find parking | Decisions on vehicle type are dependent on behaviour change and financial circumstances.
1m | Explore Park and stride. Park and ride and travel interchange. | Alternatives to private vehicle use | Bus based Park & Ride using existing routes | 2022 | 2027 | City Services including transport planning, air quality and parking, working with planning and bus operators and landowners | BHCC City Services | NO | Partially Funded | £50k - £100k | Planning | Estimated to be 3 to 5µg/m3 NO2 along shuttle routes if diesel vehicles are not used. | Identification of potential sites, reduced vehicle trips and emissions, improved roadside air quality in AQMAs | Feasibility of sites ongoing. | Identifying and establishing suitable site(s). Use existing bus routes. Lack of suitable land to develop within geographical confines of city
1n | Explore Workplace Parking Levy | Promoting Travel Alternatives | Workplace Travel Planning | 2022 | 2027 | City Services and local businesses | BHCC City Services | NO | Not Funded | £10k - 50k | Planning | Estimated to be <1µg/m3. | Reductions in vehicle commuting to increase in active travel and public transport usage | None.
1o | Liveable City Centre (LCC) | Policy Guidance and Development Control | Other policy | 2022 | 2027 | BHCC City Services | BHCC City Services & Planning | NO | Partially Funded | £100k - £500k | Planning | Trace levels | Development of design codes to identify requirements for the physical development of area to deliver improved public realm. | Baseline analysis underway | Could includeAQMA1-A2010 and bus-ULEZ but not proposed for AQMA1 A23 & A270
1p | 20-minute or fifteen minute neighbourhood | Other | Other | 2022 | 2027 | BHCC City Services | BHCC City Services & Planning | NO | Partially Funded | £50k - £100k | Planning | Trace levels. Could help manage movement of vehicles and prioritisation of space. | Less vehicle movements reduced emissions, increased active travel. | Pilot project
1q | Develop re-wilding and tree planting areas and parklets, reduce fire and smoke risk of the habitat | Other | Other | 2022 | 2027 | BHCC City Services | Sustainability and Planning | NO | Funded | £100k - £500k | Implementation | Trees and habitats more likely to help mitigate particles and dust than nitrogen dioxide. | Increased tree and vegetation planting, improved natural environment and safer more attractive places for walking and cycling | Valley Gardens, Waterhall rewilding, Carden Hill tree planting and parklets | Trees and ecosystems likely to benefit from clean air. Roadside summer foliage unlikely to mitigate nitrous pollution at roadside where >10,000 vehicles pass a day.
2a | Working towards a zero-exhaust council fleet for vehicles and machinery | Vehicle Fleet Efficiency | Other | 2022 | 2027 | BHCC Fleet Management | BHCC | NO | Funded | £1 million - £10 million | Implementation |  | Increased proportion of Zero Emission vehicles in council fleet | 2023 included 2 additional refuse vehicles, 4 communal bin lorries, 1 top loader and 6 cars. Fleet now includes 72 EVs. | Investment required to continue. Upgrade to power required at the Hollingdean Depot to add more electric vehicles
Estimated 1 to 2 µg/m3 long term reduction in roadside NO2 along some roads in AQMAs. Exemplar to other operators to explore and implement a cleaner fleet without emissions.
2b | Ultralow and zero emission zone for buses and associated improvements | Vehicle Fleet Efficiency | Other | 2019 | 2027 | BHCC City Transport, Public Transport Team, Bus Operators | BSIP (DfT), DEFRA AQ grant, BHCC and bus operators | YES | Funded | £1 million - £10 million | Implementation Bus and Minibus Exhaust Retrofits completed | Monitored 79 µg/m3 reduction in NO2 at North Street kerbside past ten years. 32 µg/m3 reduction at façade during the same period. Estimated at least 25µg/m3 reduction at North Street façade due to ultra-low or zero vehicles (buses and taxis). | Promoting ultralow and zero emission public transport | Last few remaining euro-V buses operated on time-tabled bus routes, scheduled to be retired by September 2024 at the latest. Confirmation required this applies for the bus-ULEZ and citywide. ZEBRA2 funding bid for 16 electric buses was successful. ZEBRA3 adds to this. | Buses and coaches not used for time-tabled routes, such as tourist services, rail replacement and driver training could be older and have higher emission rates that do not comply with zero or bus-ULEZ. This is a small proportion compared to the regular 300+ buses used on frequent time-tabled routes.
2c | Exhaust retrofit of middle age buses (oldest vehicles retired first) | Vehicle Fleet Efficiency | Promoting Low Emission Public Transport | 2013 | 2023 | BHCC City Transport, Public Transport Team, Bus Operators | DfT Clean Bus Transport Fund, DEFRA Air Quality grant | YES | Funded | £1 million - £10 million | Completed Late 2023 | Contributory factor in the above measured improvement | Improved air quality, bus-ULEZ compliant bus fleet. | 150 double-deck and minibuses retrofitted. Series of projects completed. | Next step is to increase percentage of the fleet (buses and taxis) that are zero emission (without exhaust). Essential to cease further procurement of diesel buses.
2d | Better aligned wheel tracking | Vehicle Fleet Efficiency | Fleet efficiency and recognition schemes | 2022 | 2027 | BHCC City Services and Imperial University of London | University | NO | Partially Funded | £50k - £100k | Planning | 1 to 2 µg/m3 PM2.5 | Reduced particulate emissions. | Preliminary discussion with bus operator and university no resource to take further since 2024, to be reiveiwed | Monitoring potential benefits causality hard to prove.
2e | Ultralow or zero emission zone for all vehicle types | Promoting Low Emission Transport | Other | 2023 | 2027 | BHCC City Services | BHCC | NO | Not Funded | £1 million - £10 million | Monitoring compliance with ULEZ | Target: 100% compliance with bus-ULEZ Euro-VI emission standard and increasing proportion of zero emission vehicles | Improved air quality, reduced vehicle journeys, increased active travel journeys | Network of vehicle category cameras installed 2024 indication of current and changing pattern of fuel types. | Benefit diminishes as a higher proportion of vehicles achieve ULEZ standards without direct intervention
2f | Promoting e-cargo bikes | Freight and Delivery Management | Other | 2020 | 2027 | BHCC City Services | BHCC (Carbon Neutral Fund) | NO | Funded | £100k - £500k | Implementation | 1 to 2 µg/m3 depending on the number of diesel vehicle trips saved | Reduced vehicle use in AQMAs and increased cycle use | More than thirty businesses switched from petrol and diesel delivery vehicles | Continuation of funding required, as cost and benefit improve.
2g | Geo-referenced hybrid buses | Vehicle Fleet Efficiency | Promoting Low Emission Public Transport | 2018 | 2027 | BHCC City Services, Bus Operators, Ricardo, University of Sussex | Bus Operators and Innovate UK | NO | Funded | £1 million - £10 million | Completed | Estimated 1 to 7 µg/m3 NO2 saved in areas targeted for hybrid zero capable | AQMA NO2 reduction along bus scheduled bus routes |  | Not available for the full regular bus fleet about 300 vehicles. Further zero emission buses scheduled for 2026.
54 double deck buses zero capable since late 2019. Used in AQMAs except the Lewes Road corridor. Also used on Upper North Street during the 2023 eastbound diversion.
2h | Fast and rapid electric chargers for vehicles (taxis, cars and vans) | Transport Planning and Infrastructure | Public transport improvements-interchanges stations and services | 2019 | 2027 | BHCC City Services, Parking | Office of Zero Emission Vehicles and City Services, Parking | NO | Funded | £130 million | Implementation | Estimated 1 to 3 µg/m3 NO2 as the proportion of vehicle trips that are zero increases | Inclusive on-street facilities. | Secured Local Electric Vehicle Infrastructure (LEVI) funding the largest level 1 contract | Funding committed to 2040. BHCC progressing to one of the top authorities in the UK for EV charging facilities.
2i | Zero exhaust emissions for last mile deliveries | Freight and Delivery Management | Freight Partnerships for city centre deliveries | 2022 | 2027 | BHCC City Services, Planning | SMEs | NO | Not Funded | £500k - £1 million | Implementation | Estimated 1 to 5 µg/m3 where roadside NO2 is high. | Reduced diesel emissions from lorries in AQMAs | Increased use of e-bikes and e-vans for deliveries. | Funded e-cargo bike project helps to facilitate this measure.
2j | Anti-idling | Environmental Permits | Introduction/increase of environment charges through permit systems and economic instruments | 2023 | 2027 | BHCC Environmental Enforcement | BHCC Environmental Enforcement | NO | Funded | £50k - £100k | Completed | 1 to 2 µg/m3 NO2 long term much more short term | Increased public awareness re: cleaner vehicles and impacts on health | Committee approved enforcement in June 2023 to start January 2024. Signage updated. Enforcement Team ask vehicles to be swiched off. Regulatory enforcement in place via FPN’s. | Barriers to implementation overcome. At least one fine issued to a persistent offender.
2k | Explore emissions-based parking charges | Environmental Permits | Introduction/increase of environment charges through permit systems and economic instruments | 2022 | 2027 | BHCC City Services, Parking | BHCC City Services, Parking | NO | Partially Funded | £50k - £100k | Planning | 1 to 2 µg/m3 NO2 long term | Fewer high NOx vehicle trips in the city | Citywide parking review underway | Requires consideration of Euro emission standards and zero emission capability, rather than be solely based on vehicle taxation band and CO2.
3a | Air quality monitoring and public reports. | Public Information | Via the Internet | 2012 | 2027 | BHCC City Services, Air Quality | BHCC City Services (Carbon Neutral Fund), DEFRA AQ grant | YES | Funded | £100k - £500k | Implementation | 1 µg/m3 NO2 long term | Increased awareness of air quality and progress in improvements | BHCC Annual Status Reports submitted to DEFRA on time every year and regular communications/messaging issued. Real-time new for 2024 | Requires earlier issue of ASR templates than April to start drafting and engaging on reports sooner. Contractors to complete data ratification earlier in the year
3b | Real-time sensors | Public Information | Via the Internet | 2022 | 2027 | BHCC City Services, Air Quality | BHCC City Services, Air Quality | YES | Funded | £100k - £500k | Completed | 1 to 2 µg/m3 PM2.5 long term | Increased awareness of AQ levels and forecasts e.g. number of website hits | Procurement completed and network operational since August 2024 | Fifty sensors installed as planned. Additional costs of installing sockets on lamp columns/installing new posts and solar panels
3c | Community Engagement at schools and events | Public Information | Other | 2019 | 2024 | Sussex Partnership and Sustrans | DEFRA AQ grant and AQ officer | YES | Funded | £50k - £100k | Completed | 1 µg/m3 NO2 long term | Improved awareness of children and adults | Engagement with schools and events countywide, final report delivered | No funding to continue. Further engagement relates to measure 3b.
3d | Communication on reducing domestic smoke | Public Information | Via the Internet | 2012 | 2027 | BHCC City Services, AQ and communications | BHCC City Services, AQ, Regulatory Services and Communications | NO | Partially Funded | £10k - 50k | Implementation | 1 µg/m3 PM2.5 long term | Reduced smoke complaints, improved air quality, greater use of cleaner home heating | Seasonal communications and officer training. Clean Air night promoted – each year. Active engagement by Regulatory Officers within SCA’s | Seek cleaner options without emissions to air.
3e | Public information campaign on air quality and health | Public Information | Via the Internet | 2022 | 2027 | BHCC City Services and public health | BHCC City Services, AQ and public health | NO | Funded | £10k - 50k | Implementation | 1 µg/m3 PM2.5 long term | Improved awareness of children and adults | Feedback to Sussex asthma children’s network, health protection screening forum and the health and wellbeing board and input to JSNA | Regular partnership working with public health consultants and the DPH team
3f | Promote Air-alert | Public Information | Via the Internet | 2012 | 2024 | Sussex AQ Partnership | Sussex Air | NO | Funded | < £10k | Completed | relates to avoiding exposure | Number of subscribers | Established | AQ index and colour scheme requires modernisation to align with AQAP targets
3g | Move for change campaign | Public Information | Other | 2019 | 2027 | BHCC City Services, Transport Planning | BHCC City Services, Transport Planning | NO | Funded | £10k - 50k | Implementation | Encourages active travel as an alternative for some journeys | Increased walking, wheeling and cycling | Continued public engagement via the Betterpoints app | Opportunity to tie in with real-time project measure 3b
4a | Ensure development has positive influence on AQ | Policy Guidance and Development Control | Air Quality Planning and Policy Guidance | 2022 | 2027 | BHCC City Services, Air Quality and Planning | BHCC as Local Planning Authority | NO | Partially Funded | £1 million - £10 million | Implementation | 1 to 7 µg/m3 NO2 | Design that achieves better than negligible impact and avoids emissions | Reduced parking spaces, increased charging points, electric heating systems for communal and domestic developments | Development needs to continue to improve the city’s environment
4b | Improve street air flow (ventilation) entrain fresh air and avoid enclosure of emissions | Policy Guidance and Development Control | Air Quality Planning and Policy Guidance | 2022 | 2027 | BHCC City Services, Air Quality and Planning | BHCC as Local Planning Authority | NO | Partially Funded | £1 million - £10 million | Implementation | 2 to 5 µg/m3 NO2 | Air quality mitigation on developments is standard. | Ensuring good design avoids creating or reinstating street canyons by designing gaps and setbacks | Delivering high density development in constrained locations and providing public amenity space
4c | Construction Environmental Management Plans (CEMPs) | Policy Guidance and Development Control | Air Quality Planning and Policy Guidance | 2021 | 2027 | BHCC City Services, Transport & Highway Development and Planning | BHCC as Local Planning Authority and Local Highway Authority | NO | Funded | £100k - £500k | Implementation | 1 to 2 µg/m3 PM2.5 and NO2 | Reduction of HGV emissions in the AQMA and reduced use of diesel generators | Ensuring use of Euro-VI HGVs, and route plans take account of AQMAs | Ensuring compliance with CEMP requirements
4d | Improved emission standards for Non-Road Mobile Machinery | Policy Guidance and Development Control | Regional Groups Co-ordinating programmes to develop Area wide Strategies to reduce emissions and improve air quality | 2022 | 2027 | BHCC City Services and Planning, Sussex Air | BHCC | NO | Partially Funded | £100k - £500k | Implementation | 1 to 4 µg/m3 PM2.5 and NO2 | Reduced emissions, reduced complaints | Conditions applied to major planning applications | Funding required to enforce more stringent standards in 2025. More ambitious comments on planning applications.
4e | Adoption and application of planning policy | Policy Guidance and Development Control | Air Quality Planning and Policy Guidance | 2022 | 2027 | BHCC City Services, Air Quality and Planning | BHCC as Local Planning Authority and Local Highway Authority | NO | Funded | £50k - £100k | Completed | 1 to 3 µg/m3 NO2, especially development areas and special areas | Adoption of City Plan Part1 and Part 2 and planning polices | Review of city design code paused due to City Council’s Financial Position | A number of policy hooks to reduce development control impacts and achieve positive benefits to reduce emissions and local air quality
4f | Development provides facilities to promote active and zero emission travel | Policy Guidance and Development Control | Other policy | 2022 | 2027 | BHCC City Services and Planning, Sussex Air | Developer | NO | Funded | £100k - £500k | Completed | 1 to 2 µg/m3 NO2 | Reduced emissions, increased active travel journeys |  | Typically, new developments include bicycle parking
Facilities to mitigate impacts and support active travel are secured on-site or via Section 278 Agreements and CIL for off-site works
4g | Ensure certain developments produce a travel plan | Policy Guidance and Development Control | Other policy | 2022 | 2027 | BHCC City Services and Planning, Sussex Air | Developer | NO | Funded | £100k - £500k | Implementation | 1 µg/m3 NO2 | Reduced emissions, increased active travel journeys | Travel plans secured as part of planning permissions | Ensuring compliance with planning conditions and monitoring requirements
4h | Ensure development meets Part S of the Building Regulations for electric vehicle charging points | Policy Guidance and Development Control | Air Quality Planning and Policy Guidance | 2022 | 2027 | BHCC City Services and Planning, Sussex Air | Developer | NO | Funded | £100k - £500k | Implementation | 1 to 2 µg/m3 NO2, rising to more as uptake of EV increases and diesel diminishes | Reduced emissions, increased uptake of EVs | Conditions applied to planning permissions | Legislation introduced in 2021
4i | Ensure major developments avoid emissions in accordance with energy hierarchy for net carbon and avoid oxide of nitrogen emissions in and around AQMAs | Policy Guidance and Development Control | Air Quality Planning and Policy Guidance | 2022 | 2027 | BHCC City Services, Air Quality, Sustainability and Planning | Developer | NO | Funded | £500k - £1 million | Implementation | 1 to 2 µg/m3 NO2 | Continued reduction in emissions and air quality indoors and outdoors | Provision secured to ensure cleaner developments for vehicles and energy prioritise non combustion renewables | Work towards 2025 Future Home Standards
Indoor and outdoor ventilation. Improve energy efficiency with building fabric upgrades. decarbonisation of home heating.
4j | Smoke control, cleaner home heating and waste disposal to avoid burning | Public Information | Via the Internet | 2022 | 2027 | BHCC Regulatory Services and Environmental Enforcement | Regulatory Services | NO | Partially Funded | £10k - 50k | Implementation | 1 to 4 µg/m3 PM10 short term | Reduced particulate levels, increased awareness of smoke | Discussions with DEFRA. Legal and Trading Standards DEFRA survey on public perceptions | New legislation in 2021, followed by further guidance.
4k | Better citywide smoke control, training for officers to enforce domestic smoke | Policy Guidance and Development Control | Other policy | 2022 | 2027 | BHCC Regulatory Services and Environmental Enforcement | DEFRA for LAs with SCAs | NO | Partially Funded | £10k - 50k | Planning | 1 to 4 µg/m3 PM10 short term | Reduced particulate emissions, reduced smoke complaints | Officer participation in DEFRA training. Promotion of clean air night. Cosy killer campaign to discourage solid fuel burning amongst highest density housing. | Limited funds available from 2023 to 2025
4l | Reduce or avoid emissions due to events and street vendors in the city | Environmental Permits | Other | 2022 | 2027 | BHCC Event Management | Permit process | NO | Partially Funded | £50k - £100k | Implementation | 1 µg/m3 NO2 and 1 to 2 µg/m3 PM2.5 short term | Reduced complaints, reduced lorry and van emissions and firework use |  | Grants required for larger events for example increased sub-station capacity The Level and Preston Park
Infrastructure installed in event locations (plugged-in places that do not have emissions to air). Drone displays instead of fireworks (which include smoke and metals)
4m | Alternatives to gas, diesel, biomass, oil, and coal combustion including ultra-low NOx gas boilers. Avoid the impacts of chimneys and flues. | Policy Guidance and Development Control | Air Quality Planning and Policy Guidance | 2018 | 2027 | BHCC City Services, Air Quality and Planning | Development Control | NO | Funded | £50k - £100k | Completed | 2 to 5 µg/m3 NO2 citywide (less in the South Downs National Park) | Increased number of ultralow emission boilers and zero emission alternatives such as electric | Seek avoidance of gas, biomass, oil, diesel, coal combustion in and around AQMAs. | Opportunities for residents and non-domestic properties to come off fossil fuel. School conversion from gas boilers to air source heat pumps. No new planning permissions for biomass or fossil fuel combustion. Swimming pool upgrade, aiming to be without combustion.
4n | Shoreham gas fired power station EPR part-A permit to control emissions | Environmental Permits | Large Combustion Plant Permits and National Plans going beyond BAT | 2012 | 2027 | Environment Agency | Permit fee | NO | Funded | £50k - £100k | Completed | 1 to 2 µg/m3 NO2 West Portslade | Permit renewed | Established permit process (pre-dates 2012 the earliest date in the DEFRA table). | Permit conditions for NOx. Consultation on investment to extend life of major gas combustion near AQMA3
4o | Two Crematorium EPR, part B permits to control emissions | Environmental Permits | Measures to reduce pollution through IPPC Permits going beyond BAT | 2012 | 2027 | BHCC Regulatory Services | Permit fee | NO | Funded | < £10k | Completed scope for further improvement | 1 µg/m3 NO2 & >1 µg/m3 PM2.5 in the vicinity of Woodvale crematorium | Permit renewed annually. Reduced mercury emissions. Woodvale seeking to install abatement plant to align with BAT and GN | Established annual process. | Include contributions in detailed AQ assessment. Aim to explore electrification of crematoria.
5a | Partnership Working Internal | Other | Air Quality Planning and Policy Guidance | 2022 | 2027 | BHCC Air Quality, Transport, Communications, Education, Regulatory Services, Public Health, Environmental Enforcement | BHCC, Air Quality | NO | Funded | £50k - £100k | Implementation | N/A | Successful collaborative working that achieves the relevant goals in the Council Plan 2023-2027 and reduces emissions. | Continuation of regular meetings BHCC Transport, Air Quality and Public Health officers | Availability of resources required to deliver continuous improvement and undertake air quality assessment
5b | Partnership Working External | Other | Via the Internet | 2022 | 2027 | BHCC Air Quality, Contractors, Universities, Sussex Air, Bus Operators, Environment Agency, DEFRA, DfT, National Highways, NHS | Sussex AQ Partnership | NO | Funded | £10k - 50k | Implementation | N/A | Regular Sussex Air Quality Partnership meetings, successful DEFRA funding bids |  | Requires revenue for officer time, to access and manage funding and collaborate with partners
Delivered at a local authority level since the mid-1990s Joint ventures help to support and deliver economies of scale and funded projects. New data management contract scheduled for later 2025
5c | Continue to lobby government to adopt 2021 WHO guidelines for PM2.5 and NO2 or EU interim targets in order to continue progressive improvement in air quality where people live. | Other | Other | 2022 | 2027 | BHCC, Air Quality leading Sussex partners. Working with DEFRA's local authority advisory group on air quality. | BHCC, Air Quality | NO | Funded | < £10k | Implementation | N/A | Adoption of health-based EU and WHO guidelines and health protections by government. Cleaner air for infirmaries recommended for devolved administrations | Responses to consultations on future air quality standards and reporting processes. Real-time network will provide awareness of most recent concentrations and daily variations. | Requirement for reporting long term air quality to compare against health protections. Exemplar authorities include GLA, Greater Oxford and Cambridge.